Figure 3-1: Timeline for ACT Organizational Activities

ACT Organizational Development

Implementation Checklist

Accessible Coordinated Transportation

of the Pikes Peak Region			   Date of this revision: 2/2/2011

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Establishing Documents |
| Bylaws are in place and are acceptable to all members | Preliminary bylaws need to be amended | Members review current bylaws and identify issues Samples of how agency can handle items needing unanimous consent versus majority consent. | ACT Board of Directors Consultant | Bylaws have been reviewed and draft language suggested for consideration at Jan 5 meeting. Discussed consent options at Nov. 3 meeting. |
| Agency Membership – Initial | In process | Have member MOUs prepared; Obtain agency signatures | Consultant | Decided at Nov. 3 meeting to use MOU format. Drafts are prepared. |
| 501(c)(3) Status | Complete | Are any corrections needed? | Secretary to Board | In February, set plans for reporting and tax filing. |
| Records | In process | Set up format for minutes and resolutions. Establish files for the organization. | Secretary to Board and future staff | Initial members have notebooks. Establish systems for keeping minutes, making resolutions, setting policies, & member notices. |
| Budget |
| Develop 2011 Budget | Not started |  | All ACT members | Will be based on activities undertaken Initial 2011 budget should be defined and adopted ASAP. See timeline. |
| Member agencies adopt budget | Not started |  | All ACT members |  |
| ACT adopts budget | Not started |  | All ACT members |  |
| Monitor revenues & expenses | Not started |  | Board Secretary / staff |  |

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Staffing |
| Identify staffing requirements and job description | Not started | For ACT management For projects Joint Dispatch Medicaid billing Other | Board President (ACT Management) SK Transportation Coordinator CI representative (Medicaid billing) | Define specific tasks, standards of work, skills, abilities, and knowledge required for job. |
| Seek funding for staff | Not started | Letter of intent sent in for CMAQ funding. Apply to City, CDOT for 5310, 5316, 5317 funds. | Board President | Identify funds to use as match |
| Process is in place for evaluation of staff and board | Not started | First annual Board evaluation cycle in 2012. | Board President | Identify process from an existing member agency and adapt to meet needs of ACT |
| Policies and Procedures |
| Adopt policies to meet funding agency standards and procedures to assure member agencies have policies in place. | Not started | Could an existing agency provide its policy manual text for updating? | Board President | Include all elements required for each funding source (FTA, OAA, PPRTA, Medicaid, etc.). Review current agency contractual clauses to identify those needed for each fund source or contract. |
| Establish Personnel Policies | Not started |  | Board Secretary | Use policies of an existing member as a base, revising to serve the needs of ACT. See also the first item in this section. |
| Establish confidentiality policies for program and IT system and has staff and volunteers sign them. | Not started | What does each agency have in place presently? | SK Director |  |
| Determine routine reporting for ACT and for funding agencies | Not started | Develop consistent definitions for cost and service items | Board President / future staff | This will be refined as more operations are conducted jointly. Revise annually. |

| Activity | Status | Follow-up Activities | Responsibility | Notes |
| --- | --- | --- | --- | --- |
| Vision, Mission, Goals & Objectives |
| Develop a vision and mission statement. | Draft prepared |  | All ACT members | Draft is included in implementation plan. A consensus and ACT adoption is needed. |
| Develop goals, strategies. And objectives | Draft prepared | Format is a timeline with narrative description of planned activities. | All ACT members | Draft is included in implementation plan. Final decisions, consensus, and Board action is needed. |
| Implement a process to review progress in meeting goals/objectives and for annual update of goals and objectives. | Not started | Solicit input from broader community. | All ACT members. | Establish process for regular progress review in 2011. First update of goals and objectives planned for 2012. |
| Financial Management |
| Financial system is set up with a separate checking account and separate set of books | Plans are in place to open a checking account | Complete checking account; Set up bookkeeping system; | Board President | The system can be managed by a bookkeeper or someone on staff at one of the agencies. Include booking of contributed time by agency staff (paid by agencies) and volunteer time (log as in-kind). |
| A budget process is in place for July 1 – June 30 fiscal year. | Bylaws do not clearly define. | Identify process that will work in sync with members budgeting processes. | All ACT members | Covers adopting an annual budget, monitoring expenditures and revenues, and making adjustments if needed. |
| Apply for funding | Letter of intent submitted for CMAQ funds. | Seek 5310/16/17 mobility management, 5311 planning, or 5304 planning funds | Board President / Board Sec./Treasurer | Funding needed for staffing. Full time desirable, half time acceptable in first year only. Funding needed for professional assistance with RFP. |
| Financial compliance and quality control procedures are in place. | Not started |  | Board Sec./Treasurer / future staff | Identify practices at one of existing member agencies to use as a base and modify to meet the needs of ACT. |
| Financial system has successfully completed one financial review and made any recommended improvements | Anticipated after end of 2010-11 fiscal year. |  | Board Sec./Treasurer / future staff | Complete any improvements prior to end of December, 2012. |

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Cost Accounting |
| Participating agencies have identified similarities and differences in systems | Not started |  | Future Staff | Address cost accounting, funding, and reporting systems/ |
| Adjustments have been made for consistent reporting | Not started |  | Future Staff | Consistency only needed in areas where it is important for cost sharing. |
| Cost-sharing agreements or purchase of service agreements are in place. |  |  | Future Staff | Address issue on what is included as an overhead expense, what are direct passenger or vehicle expenses, and how each are treated. |
| Outreach & Organizational Development |
| Establish communication channels | Not started | Determine various means and order for implementing. | Future Staff | Establish mailing list of potential partner agencies, advocates, others. Might include electronic newsletter, web page, other |
| Process is in place to solicit comments from broad group of agencies and consumers. | Not started | Determine various means and order for implementing. | Future Staff | May include both informal and formal comments. Goals are to have meaningful involvement in decision-making processes and for ACT Board to have good understanding of community needs. |
| Apply for membership on CCOST, other entities | Not started | Determine who will represent ACT as needed. | Board President |  |
| Roles, Relationships, and Responsibilities |
| Establish MOU with Mountain Metro defining partnership | Not started | Define parameters; meet w/ City staff to obtain their views | Board President | Development of MOU will be done jointly with City. |
| Establish MOU with PPACG defining partnership, resource sharing, and responsibilities | Not started | Define parameters; meet w/ PPACG staff to obtain their views | Board President | Development of MOU will be done jointly with PPACG. |
| Expand Board to represent larger portion of community | Not started | Will require building confidence in ACT among community organizations. | Board President | May initially include working with CCOST; Expansion of board will take time, as ACT shows accomplishments and intention to serve all agencies and consumers in service area. |

Figure 4-1: Timeline for Joint Call, Scheduling, and Dispatch Center

Joint Scheduling and Dispatch Center

Business Plan Checklist

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Funding and Initial Implementation Plan |
| Obtain financing | Complete | Funding received for base system | Silver Key Executive Director | $80,000 available via PPACG from Sec. 5310 $322,300 FASTER funds |
| Identify initial budget options | In process | Rough costs identified | Silver Key Executive Director | Costs for operating and capital will be refined and priorities established. |
| Initial scheduling & dispatch center functionalities Other program activities Long-term program activities | Complete | Implementation Plan includes functionalities and related activities | PPACG Mobility Manager | Adoption by CCOST, PPACG, and ACT Board Task Force members identified priorities for additional coordination activities. These are included in plan but not detailed. |
| ACT establishes technical working group | Not started | Set-up a technical working group | Silver Key Transportation Director leads | Responsibilities include making recommendations to Silver Key (and other agencies as appropriate) on technical and process aspects of joint call, scheduling, and dispatch center |
| Functions and Equipment |
| For each functionality, identify the details and equipment needs. Functions: Information / Assistance Reservations Scheduling Dispatch Billing Recordkeeping/reporting | General info is included in the implementation plan. Not started on specifics | Identify and compare existing systems at each provider. Address internal systems and those that affect customer – e.g., are trips scheduled when requested, within 24 hours, or other? How are will-calls handled? Document desired practices. | Technical Working Group. Silver Key Transportation Director leads. Participants are: SK IT staff; dispatch from DSI, FVSC, RMHS, CC, and others as interested; Board reps from DSI & FVSC; PPACG Mobility Manager | It is recommended that practices at Metro Mobility also be examined. Others may need to assist on reporting and billing functions This task will help to determine what needs to be included in RFP and questions to ask vendors. |

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Identify technology needed for each functionality | Not started | Document communication system, software, and computer systems at Silver Key | Silver Key IT staff | Basic technology is discussed in implementation plan. Prioritize importance of various features as they relate to software and equipment. |
| Identify vehicles for AVL and MDT | Not started | List specific vehicles. Note any to be replaced over time of installation. | Silver Key Transportation Director | Will volunteer drivers use MDTs? May be desirable to test appropriateness. If not, identify back-up plan. |
| Protocols and Practices |
| Information, Referral, and Options: Call-Taking Guide |
| Identify number of lines and how they will be answered. | Not Started |  | Technical Working Group | How many lines are needed? Can existing lines be forwarded to dispatch center? |
| Identify text for answering each line. | Not started |  |  | Training manual template has been provided |
| Protocol for updating and sharing information | Not started |  |  | Lisa / Lori assist as well Address for before and after there is a single system. |
| Customer Responsibility Standards |
| Standards for no shows, late cancellations, etc. | Not started | Identify and compare existing terminology and rules at each provider. Recommendations made for agency consideration | Technical Working Group | Identify any variation that can be (or needs to be) accommodated. Adoption of common standards can occur before CAD system is in place, but final decisions should wait until procurement is completed. |
| Agency consideration, adoption | Not started |  | Agency directors |  |

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Fare and Donation Policies |
| Document similarities and differences in donation and fare policies, collection practices, and reporting procedures. | Not started | Identify and compare. Make recommendations for agency consideration | Technical Working Group | Identify any variation that can be (or needs to be) accommodated. Adoption of common standards can occur before CAD system is in place, but final decisions should wait until procurement is completed. |
| Agency consideration, adoption | Not started |  | Agency directors |  |
| Eligibility / Cross Eligibility Practices |
| Document existing program eligibility practices | Underway | Lisa has collected information on agency application forms | Technical Working Group | Procedures for written applications and verbal information collection need to be defined. |
| Identify procedures needed for other programs | Not started | Investigate eligibility information needed for Veterans’ programs, Medicaid NEMT, HCBS, etc. | Technical Working Group |  |
| Recommend procedures for intake | Not started | Obtain public | Technical Working Group | Procedures can be used by agencies before full transition. Coordinate with call-taking guidelines and common client database procedures. |
| Determine time frame and transition plans; implement | Not started |  | Technical Working Group |  |
| Recordkeeping and Reporting |
| Current practices | Not started | Document service, ridership, and financial reporting. | Technical Working Group |  |
| Desired changes / equipment and software impacts | Not started | Identify improvements desired by providers, funders Identify impacts on equipment and software | Technical Working Group | Additional information desired to: Show how specialized services augment (not compete with) Mountain Metro Transit services. Monitor cost components of services (i.e. dispatch, service provision, etc/) |

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Recommendations to ACT | Not started |  | Technical Working Group |  |
| Client Database |
| Determine existing data by agency | Not started | Each agency provides list of fields, format, and sample data | Technical Working Group | What source documents are used to enter client data? What format is each database in presently? |
| Determine what fields are needed for master database | Not started | Format for final product? (Spreadsheet or database) | Technical Working Group | Identify what Metro Mobility uses as well as existing providers. Consider what may be needed for Medicaid NEMT and HCBS as well as Vet status. |
| Each agency updates their list | Not started | Delete old records, complete missing fields | Each agency | . |
| Identify protocol for maintaining list. | Not started | Frequency and responsibility for cleaning Method of transferring data until there is a single system. | Technical Working Group |  |
| Create master list, removing duplicates | Not started |  | Technical Working Group | Lead responsibility is expected to fall to Silver Key. |
| Procurement |
| Refine list of specific functions and base network desired (hardware and software). | In process. Base information is in implementation plan | Update list based on development of protocols. Solicit comments from CCOST, others. | Technical Working Group | This will be helpful for clear communications and as a guide for technology firms to use in illustrating their wares. |

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Review 3-5 software programs | Done once, will be re-done for more specific information | Identify firms the working group wishes to learn more about | Silver Key IT staff. CDOT Region 2 transportation staff may assist. | For each function and network requirements, leave with a clear understanding of how the software accomplishes task, options for customizing, hardware & communications requirements, etc. Identify any details that need to be included (or left out) of RFP to enable each firm to bid. |
| Determine if consultant support is needed to complete RFP. | Not started |  | Silver Key IT staff. CDOT Region 2 transportation staff may assist. | Consider requirements in next three tasks, time frame for preparing, and available skills/time of participants. |
| Identify specific requirements for software and hardware. | Not started |  | Silver Key IT staff. CDOT Region 2 transportation staff may assist. | Identify what equipment is needed, what is available. Specify items necessary and desired in scope of work. |
| Determine desired phasing installation of components and agencies | Not started | Identify options and consider advantages & disadvantages of each. | Technical Working Group | Discuss options with vendors, agencies |
| Prepare specifications for software, hardware, installation, and training | Not started | Identify time frame and responsibilities. If professional support used, allow for solicitation | Technical Working Group | Will be broken into logical bundles |
| Conduct procurement process | Not started |  | Silver Key |  |
| Purchase, install and test system | Not started |  | Silver Key |  |

| Activity | Status | Follow-up Activities | Responsibility | Notes: |
| --- | --- | --- | --- | --- |
| Agency Agreements |
| Set up project accounting in a manner that documents all contributions and builds an understanding of both costs and (over time) the savings that occur. | Not started | Document time contributed by other agencies and volunteer time (board members) | SK Finance | The value of this can be used as in-kind contributions to match grants. |
| Determine cost share arrangements prior to system being fully combined and after joint operations begin. Determine how long-term costs will be shared. | First steps taken | Initial decision to have staff from DSI and FVSC work out of SK part of the time has been made. Work out details. Evaluate and determine long-term options. Choices include Purchase services from Silver Key Contribute staff to a combined system | SK Executive Director | Determine feasible arrangements for staff, how job duties will be accomplished and adjusted, and timing for implementing this change. Determine total costs of system with staff time and associated equipment/facilities for call taking, scheduling, dispatch, and ancillary services. Determine reasonable basis for cost share. Time spent per call for each agency. Number of dispatch contacts per month (or week). |
| Prepare agreements between agencies documenting choices. | Not started |  | SK Executive Director | These agreements will be approximately one year in term as the situation will be fairly fluid. |

Figure 5-1: Timeline for Other Coordination Activities